## Sheet1
Unique ID | User story | Story Points | Assignee | Reviewers 1 | Reviewers 2
3 | As a Member (Jest) | 15
3.1 | I want to post my personal information (Jest) | 1 | Adam Sadek | Kareem elShafey | Omar Hesham
3.2 | I want to post my qualifications, skills interests, past events, project tasks, jobs (Jest) | 1 | Adam Sadek | Kareem elShafey | Omar Hesham
3.3 | I want to view available locations on a certain date (Jest) | 1 | Adam Sadek | Kareem elShafey | Omar Hesham
3.4 | i want to be notified when a co-working space reservation is confirmed (Jest) | 1 | Adam Sadek | Kareem elShafey | Omar Hesham
3.5 | I want to able to request a larger area when I need to (Jest) | 1 | Adam Sadek | Kareem elShafey | Omar Hesham
3.6 | I want to be recommended a co-working space based on the the capacity and the location of my event when creating one (Jest) | 1 | Adam Sadek | Kareem elShafey | Omar Hesham
3.7 | I want to search for Vacancies by keywords (Jest) | 1 | Adam Sadek | Kareem elShafey | Omar Hesham
3.8 | I want to view all Vacancies (Jest) | 1 | Adam Sadek | Kareem elShafey | Omar Hesham
3.9 | I want to apply for a vacancy (Jest) | 1 | Omar Hesham | Andrew Ashraf | Adam Sadek
3.1 | I want to get notified about the jobs I applied to when its edited (Jest) | 1 | Omar Hesham | Andrew Ashraf | Adam Sadek
3.11 | I want to get notified about the jobs I applied to when its deleted (Jest) | 1 | Omar Hesham | Andrew Ashraf | Adam Sadek
3.12 | I want to get notified when i get accepted or rejected by a job i applied for (Jest) | 1 | Omar Hesham | Andrew Ashraf | Adam Sadek
3.13 | I want to delete my application to a vacancy (Jest) | 1 | Omar Hesham | Andrew Ashraf | Adam Sadek
3.14 | I want to filter Vacancies according to location, salary, daily working hours, start and end duration date, owner of the ad (Jest) | 1 | Andrew Ashraf | Adam Sadek | Omar Hesham
3.15 | I want to be recommended jobs that suits my skills, location and availability (Jest) | 1 | Andrew Ashraf | Adam Sadek | Omar Hesham
4 | As an admin (Jest) | 21
4.1 | I want to be able to delete/hide any profile due to violations of contract or agreement(Mongo) (Jest) | 2 | Muhammad Sharaf | khaled khater | mohamed ibrahim
4.2 | I want to view vacancy ad requests (Jest) | 1 | Muhammad Sharaf | khaled khater | mohamed ibrahim
4.3 | I want to view a calendar reflecting reserved places on each day (Jest) | 1
4.4 | I want to send a message to my client (Jest) | 1 | Muhammad Sharaf | khaled khater | mohamed ibrahim
4.5 | I want to recieve a message from my client (Jest) | 1 | Muhammad Sharaf | khaled khater | mohamed ibrahim
4.6 | I want to set attributes to the vacancy ad so that members can see the requirements (Jest) | 1 | Muhammad Sharaf | khaled khater | mohamed ibrahim
4.7 | I want to assign weights to every attribute (Jest) | 1 | Muhammad Sharaf | khaled khater | mohamed ibrahim
4.8 | I want to post vacancy ad requests so clients can apply for them (Jest) | 1 | Muhammad Sharaf | khaled khater | mohamed ibrahim
4.9 | I want to I want to edit vacancies (Mongo) (Jest) | 1 | Muhammad Sharaf | khaled khater | mohamed ibrahim
4.1 | I want to delete a vacancy ad (Mongo) (Jest) | 1 | Omar Mohamed | khaled khater | mohamed ibrahim
4.11 | I want a recommendation system that sorts applicants according the their attributes and the weight of those attributes (New) (Epic)
4.12 | I want to notify applicants who applied for an ad when it has been edited so they can decide if they want to pull their application or not (Mongo DB) (Jest) | 2 | Omar Mohamed | khaled khater | mohamed ibrahim
4.13 | I want to notify members when a vacancy ad they applied for is deleted (Mongo DB) (Jest) | 2 | Omar Mohamed | khaled khater | mohamed ibrahim
4.14 | I want to notify members who applied for a job and got accepted (Mongo DB) (Jest) | 2 | Omar Mohamed | khaled khater | mohamed ibrahim
4.15 | I want to notify members who applied for a job and did not get accepted (Mongo DB) (Jest) | 2 | Omar Mohamed | khaled khater | mohamed ibrahim
4.17 | I want to notify members who applied for a job and got accepted about their interview (Mongo DB) (Jest) | 2 | mohamed ibrahim | muhammad sharaf | Omar Mohamed
5 | As a partner (Jest) | 19
5.1 | I want to post my basic business information, partners, board members, event organized by my organization, my field of work and past projects (Jest) | 1 | mohamed refaat | mohamed ibrahim | Omar Mohamed
5.2 | I want to request Vacancy ad with the description of the job (Mongo) (Jest) | 2 | mohamed refaat | mohamed ibrahim | Omar Mohamed
5.3 | I want to be able to specify the details of my vacancy ad (Mongo) (Jest) | 2 | mohamed refaat | mohamed ibrahim | Omar Mohamed
5.4 | I want to view the status of the vacancy ad from the moment I requested it till I decide on a candidate (Mongo) (Jest) | 2 | mohamed refaat | mohamed ibrahim | Omar Mohamed
5.5 | I want to edit any attribute for my vacancy ad (Mongo) (Jest) | 2 | mohamed refaat | mohamed ibrahim | Omar Mohamed
5.6 | I want to delete my vacancy ad (Mongo) (Jest) | 2 | mohamed ibrahim | muhammad sharaf | Omar Mohamed
5.7 | I want to view the number of applicants who applied for my vacancy (Mongo) (Jest) | 2 | mohamed ibrahim | muhammad sharaf | Omar Mohamed
5.8 | I want to view a List of applicants ordered by the suitability for the job (Jest) | 1 | mohamed ibrahim | muhammad sharaf | Omar Mohamed
5.9 | I want to be able to send notifications to approved applicants so I can contact them for an interview (Jest) | 1 | mohamed ibrahim | muhammad sharaf | Omar Mohamed
5.1 | I want to be able to close my vacancy ad (Mongo) (Jest) | 2 | mohamed ibrahim | muhammad sharaf | Omar Mohamed
5.11 | I want to view my old vacancy ads (Mongo) (Jest) | 2
6 | As a co-working space owner (Jest) | 9
6.1 | Create Co-working Space (Jest) | 1 | Kareem elShafey | Andrew Ahraf | Youssef Samir
6.2 | View Co-working Space attributes (Jest) | 1 | Kareem elShafey | Andrew Ahraf | Youssef Samir
6.3 | Update Co-working Space attributes (Jest) | 1 | Kareem elShafey | Andrew Ahraf | Youssef Samir
6.4 | Delete Co-working Space account (Jest) | 1 | Kareem elShafey | Andrew Ahraf | Youssef Samir
6.5 | I want to post new place to be booked for future events (Mongo) (Jest) | 2 | Kareem elShafey | Andrew Ahraf | Youssef Samir
6.6 | I want to view Co-working spaces by their id (Jest) | 1 | Kareem elShafey | Andrew Ahraf | Youssef Samir
6.7 | I want to mark days that I will not be able to host any events in (Mongo) (Jest) | 2 | Kareem elShafey | Andrew Ahraf | Youssef Samir
7 | Messages (Jest) | 6
7.1 | Create message (Mongo DB) (Jest) (New) | 2 | Andrew Ashraf | Kareem elShafey | Omar Hesham
7.2 | View message (Mongo DB) (Jest) (New) | 2 | Andrew Ashraf | Kareem elShafey | Omar Hesham
| Delete message (Mongo DB) (Jest) (New) | 2 | Andrew Ashraf | Kareem elShafey | Omar Hesham
8 | Notifications (Mongo) (Jest) | 9
8.1 | Create Notification (Mongo) (Jest) | 2 | Youssef Samir | Adam Sadek | Omar Hesham
8.2 | View Notification (Mongo) (Jest) | 2 | Youssef Samir | Adam Sadek | Omar Hesham
8.3 | Update Notificatiom (Mongo) (Jest) | 3 | Youssef Samir | Adam Sadek | Omar Hesham
8.4 | Delete Notification (Mongo) (Jest) | 2 | Youssef Samir | Adam Sadek | Omar Hesham
9 | Calendar (Google Calender integration) (Automation) | 2
9.1 | I want to create a calendar reflecting reserved places on each day (Jest) | 1 | Andrew Ashraf | Kareem elShafey | YoussefSamir
9.2 | I want to update the calendar when a location has been booked (Jest) | 1 | Andrew Ashraf | Kareem elShafey | YoussefSamir
10 | Vacancies (Jest) | 5
10.1 | Create Vacancies (Jest) | 1 | Omar Hesham | Andrew Ashraf | Adam Sadek
10.2 | View Vacancies (Jest) | 1 | Omar Hesham | Andrew Ashraf | Adam Sadek
10.3 | Update Vacancies attributes (Jest) | 2 | Omar Hesham | Andrew Ashraf | Adam Sadek
10.4 | Delete Vacancies (Jest) | 1 | Omar Hesham | Andrew Ashraf | Adam Sadek
11 | Vacancy Ad (Jest) | 5
11.1 | Create Vacancy Ad (Jest) | 1 | Adam Sadek | Andrew Ashraf | Omar Hesham
11.2 | View Vacancy Ad (Jest) | 1 | Adam Sadek | Andrew Ashraf | Omar Hesham
11.3 | Update Vacancy Ad Attributes (Jest) | 2 | Andrew Adhraf | Adam Sadek | Omar Hesham
11.4 | Delete Vacancy Ad (Jest) | 1 | Andrew Adhraf | Adam Sadek | Omar Hesham
| SUM OF ALL POINTS | 91